## Sheet2
Section | Item | Rating | Comments
4.1 | Was a STFC Client appointed for all projects with sufficient resources?
Sec 3 | Were all construction projects managed under the Code 13 (or Code 15 where only one contractor)?
4.2.3 | Was a Principal Designer appointed to all projects in writing if required?
4.2.4 | Was a Principal Contractor appointed to all projects in writing if required?
4.2.8; App 3 | Were the STFC management arrangements confirmed for all projects?
4.4.5; App 4 | Was suitable and sufficient pre-construction information generated for all projects?
4.2.6; App 1; App 7 | Is there evidence that the competence of duty holders have been checked?
4.2.12; App 6 | Was a Construction Phase Plan reviewed prior to construction commencing in all projects?
4.2.7; App 2 | Was an F10 produced (if required) and displayed as required?
4.5.12 | Evidence that the Principal Contractor has managed the interface between contractor’s works and on-going STFC activities for all projects.
4.2.10; App 6 | Are Construction Phase Plans regularly updated during the construction phase to manage risk effectively?
4.5.9; App 5 | Were all contractors and visitors inducted by the STFC and the Principal Contractor?
4.3.8 | Did all Principal Contractors report all SHE incidents?
4.4.6;4.5.10; App 8 | If required, were Health and Safety Files produced as part of construction projects?
4.2.4 | Was the SHE performance of the projects reviewed on completion?